## Sheet1
Problem | ID | Estimation (Time for task) | Priority | Sprint
Group formation | 1 | N/A | 1 | 1st | 1st Sprint - weeks 1-3
Git Hub | 2 | N/A | 2 | 1st | 2nd Sprint - weeks 4-6
Code of Conduct | 3 | Ten mintues | 8 | 1st | 3rd Sprint - weeks 7-9
Travis CI | 4 | 2 weeks | 3 | 1st | 4th Sprint - weeks 10-12
Docker implmentation | 5 | 1 day | 4 | 1st
JAR | 6 |  | 5 | 1st
Maven | 7 | 1 day | 6 | 1st
First Release | 8 | Three Weeks | 7 | 1st
Integration with Zube.io | 9 | 1 day | 1 | 2nd
UML diagram creation | 10 | 2 days | 2 | 2nd
Introduction of sprint boards | 11 | 1 day | 3 | 2nd
Preparation of first 10 raports | 12 | 2 weeks | 4 | 2nd
Introduction of TDD | 13 | 1 day | 1 | 3rd
Unit tests | 14 | 1 week | 3 | 3rd
Integrating tests with Travis | 15 | 1 day | 4 | 3rd
Preparation of remaining 15 raports | 16 | 2 weeks | 2 | 3rd
Bug reporting system | 17 | 1 day | 1 | 4th
Deployment working | 19 | 3 weeks | 2 | 4th